OpenPlant Fund Application Form

Title of Project

Site-directed integration of transgenes into the nuclear genome of plants using CRISPR/Cpf1/ssDNA

Primary contact for the team

Gonzalo I Mendoza-Ochoa (gim23@cam.ac.uk), Department of Plant Sciences, Cambridge University

Team

Nandor D Hegyi (nandor.hegyi.16@aberdeen.ac.uk) – Summer student, Plant Metabolism Group, Department of Plant Sciences, Cambridge University. Nandor will perform most experiments on Chlamydomonas, including data analysis and documentation.

Gonzalo I Mendoza-Ochoa (gim23@cam.ac.uk), Plant Metabolism Group, Department of Plant Sciences, Cambridge University. Gonzalo will coordinate the project, design experiments, train and supervise Nandor and perform some experiments on Chlamydomonas.

Aleix Gorchs (ag853@cam.ac.uk), Plant Metabolism Group, Department of Plant Sciences, Cambridge University. Aleix will design experiments, train and supervise Nandor and perform some experiments on Chlamydomonas.

Payam Mehrshahi (pm579@cam.ac.uk), Plant Metabolism Group, Department of Plant Sciences, Cambridge University. Payam will contribute with knowledge and expertise on expressing transgenes in Chlamydomonas and help to design experiments.

Oleg Raitskin (oleg.raitskin@earlham.ac.uk), Nicola Patron Group, Earlham Institute, Norwich Research Park. Oleg will contribute with knowledge and expertise in use of CRISPR for plants and will perform experiments on plant protoplasts.

Quentin Dudley (quentin.dudley@earlham.ac.uk) Nicola Patron Group, Earlham Institute, Norwich Research Park. Quentin will contribute with knowledge and expertise in use of CRISPR for plants and will perform experiments on plant protoplasts.

Summary

There is great potential in using algae, including the green alga Chlamydomonas reinhardtii, for the sustainable production of high value compounds (Brodie et al., 2017). However, one obstacle in reaching that long-term goal is the limited number of gene editing and genomic transformation technologies for algae. For instance, transformation of the alga Chlamydomonas reinhardtii is via random integration and so requires extensive screening steps to isolate cell lines that stably express the transgene to high levels. To accelerate this process, we aim to establish a CRISPR/Cpf1-based technique (Ferenczi et al., 2017) to insert transgenes into specific genome sites that are predicted to promote high expression. The technique would reduce the variation of gene expression within the transformed cell population, allow high throughput testing of a large number of DNA constructs, and therefore increase our capacity to create highly productive cell lines.

Background

For most organisms studied in the subject, CRISPR/Cas9 is a method of choice for precision genome engineering. It works by delivery a two-component system inside the cell: Cas9 nuclease and either crRNA and tracrRNA or sgRNA. The sgRNA or cr/tracrRNAs guide the Cas9 nuclease and activate it on the selected genomic loci to generate double stranded DNA breaks. Customized DNA fragments can be inserted through these breaks and integrated into the genome either through the “error-prone” NHEJ pathway or homologous repair mechanisms. DNA fragments can be delivered as circular plasmids, as double stranded fragments (synthetic or PCR products) or as single stranded deoxyoligonucleotides (ssODN). The advantage of the ssODNs is less nonspecific integration events, more preferable homologous repair-based integration (Zorin et al., 2005).

In Chlamydomonas reinhardtii however, very low editing efficiency had been observed using CRISPR/Cas9 (Ferenczi et al., 2017). In last several years new CRISPR/Cas variants were discovered and characterized, largely increasing the existing repertoire of the genomic engineering tools and the pool of available genomic targets (Cpf1 – Bernd Zeitsche et al. 2015; SaCas9 – F. Ann Ran, Feng Zhang’s lab, 2015; St-Cas9 – Puchta lab used in plants; NmCas9 – Lee CM, Gang Bao group, 2016; VQR, EQR, VRER etc. – Benjamin Kleinstiver from Keith Young’s lab, XCas9 3.7 – Hu et al. David liu lab, 2017; Cms1 – Matthew Begemann, Benson Hill Biosystems, in BioRxiv). Therefore, the idea was born in the Molnar lab to test the use of ssODN as template for homologous repair, together with CRISPR/Cpf1 other than CRISPR/Cas9, for gene-editing in Chlamydomonas (Ferenczi et al., 2017).

Proposal

Ferenczi and others (2017) have recently developed a high efficient (~10%) method for knock-in of short sequences (~10-20 bp) into the genome of Chlamydomonas. The method works by delivering a ribonucleoprotein (RNP) complex of the Cpf1 nuclease and guide RNA plus a single stranded DNA (ssDNA) as template for homologous recombination. With help of Aron Ferenczi and head of group Attila Molnar (University of Edinburgh), we have successfully recapitulated this technique at the Smith lab. However, the RNP/Cpf1/ssDNA editing strategy has not been used for inserting long (e.g. 500+ bp) sequences. The aim of this project is to enhance the technique to be able to insert long sequences, coding for transgenes, into specific places of the genome. If successful we plan to try this technique for other plant systems (e.g.protoplasts of Nicotiana benthamiana and Arabidopsis thaliana) and compare its efficacy with alternate techniques using other CRISPR nucleases and double-stranded repair templates.

Objectives:

1.- Identify six genomic sites that are predicted from the literature to promote high expression of transgenes, which will be used as "landing sites" for the reporter genes. (Smith lab)

2.-Standardize a protocol for generating long (0.5-4 Kb) ssDNA, in sufficient amounts while minimizing primer contamination (this will be done in collaboration with Attila Molnar's lab). For this, we will try a PCR-based kit from Takara for generating long ssDNA. (Smith lab)

3.-Generate transcriptional units for expression of antibiotic resistance and fluorescent proteins (3) and, following a protocol established by the Molnar lab, insert these transcriptional units into previously selected "landing sites" in a combinatorial manner (18 combinations). (Smith lab)

4.-Characterize and analyse the transgenic strains to establish whether genome location and/or insert size and sequence influence insertion efficiency and/or expression level of the transgenes. (Smith lab)

5.-Once the protocol for inserting transgenes into Chlamydomonas is established, as proof of concept test whether a similar strategy can be used to insert transgenes into “landing sites” of the genome of higher plants, such as Nicotiana benthamiana or Arabidopsis thaliana (Patron lab).

Benefits and outcomes

The goal of this project is to improve a novel synthetic biology strategy for inserting genes into algae and plants genomes, which will enable production of transgenic organisms in a more precise and high throughput manner. Support from the OpenPlant fund will provide funds for the high quality regents/kits required for carrying out this project. Extensive knowledge and technology transfer between Cambridge and Norwich will be encouraged. This will be crucial for success because while team members in Cambridge have experience in Chlamydomonas transformation, transgene expression, and recently CRISPR/Cpf1/ssDNA; team members in Norwich have most experience in plant CRISPR/Cas9/dsDNA. Thus, the collaboration described here should contain the appropriate level of expertise to reach our objectives.

Sponsor for the research and cost centre

Prof. Alison Smith (as25@cam.ac.uk), Department of Plant Sciences, University of Cambridge

I confirm that I have the full support of the sponsor listed above and that they can be added to the OpenPlant Fund mailing list to receive project updates (to which they can unsubscribe at any time).

Budget

Costs for key reagents

| Item | Number | Unitary cost | total |
| --- | --- | --- | --- |
| Primers (both short and long primers) | 99 | 5 | £ 495 |
| Q5 high-fidelity polymerase (500 U) NEB | 1 | 241 | £ 241 |
| Long ssDNA Production System Takara (25 rxns) | 3 | 448 | £ 1,344 |
| TALON® Superflow™ | 1 | 114 | £ 114 |
| Phire Plant Direct PCR Kit | 4 | 194 | £ 776 |
| MEGAscript™ T7 Transcription Kit (200 rxns) | 1 | 1,026 | £ 1,026 |
| TOTAL |  |  | £ 3,996 |

References

Brodie, J., Chan, C.X., De Clerck, O., Cock, J.M., Coelho, S.M., Gachon, C., Grossman, A.R., Mock, T., Raven, J.A., Smith, A.G., et al. (2017). The Algal Revolution. Trends Plant Sci. 1–13.

Ferenczi, A., Pyott, D.E., Xipnitou, A., and Molnar, A. (2017). Efficient targeted DNA editing and replacement in Chlamydomonas reinhardtiiusing Cpf1 ribonucleoproteins and single-stranded DNA. Proc. Natl. Acad. Sci. 12, 201710597.

Zorin, B., Hegemann, P., and Sizova, I. (2005). Nuclear-Gene Targeting by Using Single-Stranded DNA Avoids Illegitimate DNA Integration in Chlamydomonas reinhardtii Nuclear-Gene Targeting by Using Single-Stranded DNA Avoids Illegitimate DNA Integration in Chlamydomonas reinhardtii †. Eukaryot. Cell 4, 1264–1272.